## Slide 1
◆
◆
SIMPLE WALKTHROUGH FOR MANAGEMENT
Our Journey, Step by Step
Nine simple steps from 'no system at all' to 'a tool the whole team relies on every day' — what's done, what's next, and exactly what's holding each step up.
DRIP Platform · Prepared for: Manager review · Maximum 10 slides, plain language throughout
Notes: Cover slide. Explain the format: nine steps, laid out like a staircase. Each following slide shows one step, whether it's done, and — if it's stuck — exactly what's holding it up and what fixes it. The little bar at the top of every slide shows all nine steps at once, so it's always clear where we are in the whole journey.

## Slide 2
1
2
3
4
5
6
7
8
9
STEP 1 OF 9
Build one system for everything
DONE
WHAT THIS STEP MEANS
Before this project, information about banks and contacts lived in scattered spreadsheets, emails, and people's memory. Step 1 was building one single system where all of that lives together.
WHY IT'S SAFE TO CALL THIS DONE
This week, we directly checked the running system while signed in: the database, the login, and the main screens all work and hold real information — not a plan, not a mock-up.
DRIP Platform — Our Journey, Step by Step
1
Notes: Step 1: the foundation. This is genuinely finished and verified live this week. No bottleneck to report here.

## Slide 3
1
2
3
4
5
6
7
8
9
STEP 2 OF 9
Load and organise our real contacts
DONE
WHAT THIS STEP MEANS
Step 2 was taking every contact we already had — from old spreadsheets and research — and loading them into the new system, organised by bank, with each person's role and importance marked.
One honest caveat: most contact emails are marked 'unverified' — that's covered in Step 6.
WHY IT'S SAFE TO CALL THIS DONE
8,000+ real contacts are loaded and organised today, each linked to their bank, with priority ranking and outreach history. Verified live this week — this is not a placeholder number.
DRIP Platform — Our Journey, Step by Step
2
Notes: Step 2: the data. 8,000+ contacts loaded and organised is real and verified. Flag honestly that they aren't independently verified yet — that's Step 6, not a gap in this step.

## Slide 4
1
2
3
4
5
6
7
8
9
STEP 3 OF 9
Make it track everything automatically
DONE
WHAT THIS STEP MEANS
Step 3 was making the system do the remembering for us: every bank's page shows its people, its deals, and any relevant news — and the system checks the news on its own, without anyone asking it to.
WHY IT'S SAFE TO CALL THIS DONE
Bank pages, the deal board, and the automatic news-watcher were all checked live this week and work as described. Contact upload and export buttons on bank pages also work.
DRIP Platform — Our Journey, Step by Step
3
Notes: Step 3: the day-to-day tools. Bank pages, deal board, and news watching are real and verified. This is the 'no more scattered spreadsheets' promise, delivered.

## Slide 5
1
2
3
4
5
6
7
8
9
STEP 4 OF 9
Let AI suggest what to do next
BUILT, NOT SWITCHED ON
WHAT THIS STEP MEANS
Step 4 was building a smart assistant that looks at everything the system knows about a contact and suggests who to reach out to next, and why — instead of the team relying on memory or guesswork.
THE HOLD-UP
The assistant is fully built and wired up, but it needs a paid subscription to a real AI provider (like the technology behind ChatGPT) to actually think. Without it, we verified this week that it returns a clearly labelled placeholder answer, not a real suggestion.
THE FIX
Buy one AI subscription. Because all the wiring is already done and tested, every AI feature across the whole system switches on at once, immediately, the moment the subscription is active. No further building required.
DRIP Platform — Our Journey, Step by Step
4
Notes: Step 4: this is the clearest 'built but not switched on' example. Say plainly: we tested it this week and it returns a labelled placeholder. The fix is a single purchase away and turns on everything at once.

## Slide 6
1
2
3
4
5
6
7
8
9
STEP 5 OF 9
Send real emails to banks
BLOCKED — WAITING ON A PURCHASE
WHAT THIS STEP MEANS
Step 5 is being able to actually send outreach and campaign emails to real bank contacts, straight from the system, with open and click tracking.
THE HOLD-UP
Sending is intentionally switched off right now, as a safety measure, so nothing goes out by mistake. Even once switched on, email providers like Gmail and Outlook only trust a sending address that has earned a reputation gradually — that trust cannot be built with code, only by sending real mail slowly over about two weeks.
THE FIX
Buy our own sending domain and an email-sending service, then run the two-week 'warm-up' period before full use. This should be started early, since the two weeks cannot be rushed.
DRIP Platform — Our Journey, Step by Step
5
Notes: Step 5: the biggest and most time-sensitive external dependency. Recommend starting the domain purchase and warm-up as early as possible since it's a fixed two weeks no matter when we start.

## Slide 7
1
2
3
4
5
6
7
8
9
STEP 6 OF 9
Confirm our contact data is correct
NOT STARTED YET
WHAT THIS STEP MEANS
Step 6 is independently double-checking that the emails and phone numbers we have for our 8,000+ contacts are actually correct and active, before we rely on them for real outreach.
THE HOLD-UP
Our contact details come from our own research, which is valuable but self-reported. There is no independent, paid verification yet — confirmed emails and phone numbers at this scale are a product only a few specialist companies sell, and they can't be reliably guessed or built in-house.
THE FIX
Subscribe to one contact-verification service. The technical work to connect it is already built and ready — turning it on takes about a week once the subscription starts.
DRIP Platform — Our Journey, Step by Step
6
Notes: Step 6: explain simply why this can't be solved with more coding — verified contact data is literally a paid product these companies sell, not something we can generate ourselves.

## Slide 8
1
2
3
4
5
6
7
8
9
STEP 7 OF 9
Move off one laptop, onto a real server
NOT STARTED YET
WHAT THIS STEP MEANS
Step 7 is moving the system from running on one person's laptop to running on a proper always-on server, so the whole team can reach it any time, from anywhere — not just when one specific laptop happens to be on.
THE HOLD-UP
Right now, if that one laptop is off, asleep, or somewhere else, the system is simply unreachable for everyone. A personal laptop cannot be turned into a 24/7 server by writing more code — it needs to be rented from a hosting company.
THE FIX
Set up one hosting account (a company decision, not a technical one) and move the already-prepared system onto it. This is expected to take only a few days once the account exists.
DRIP Platform — Our Journey, Step by Step
7
Notes: Step 7: this is the single highest-leverage next step, since Steps 8 and 9 both depend on it. Frame it as fast and low-risk — days, not weeks, once a hosting account is opened.

## Slide 9
1
2
3
4
5
6
7
8
9
STEP 8 OF 9
Get the whole team using it, every day
NOT STARTED YET
WHAT THIS STEP MEANS
Step 8 is the real test: the whole team signing in and using the system for their actual daily work, for two straight weeks, with every problem they hit written down and fixed.
THE HOLD-UP
So far, only one person has ever used the system. Every issue found — including this month's 'banks stuck on loading' — was found by one person clicking around. We also know of about 30 places in the app where a failed request shows nothing instead of a clear message, and only one of them has been fixed so far.
THE FIX
First, fix the remaining silent-failure spots (a few days of focused work). Then, once Step 7's server is live, have the whole team use the system daily for two weeks with a shared list of issues — this is the only way to really prove it works as a team tool, not just in testing.
DRIP Platform — Our Journey, Step by Step
8
Notes: Step 8: connect this directly to the 'banks stuck on loading' incident as concrete proof this step hasn't happened yet. Two clear actions: finish the silent-failure sweep, then run a real two-week team trial.

## Slide 10
1
2
3
4
5
6
7
8
9
STEP 9 OF 9
Get legal sign-off for data privacy
NOT STARTED YET
WHAT THIS STEP MEANS
Step 9 is having a qualified lawyer formally confirm that how we store and use bank contacts' personal information follows Saudi Arabia's data-protection law (PDPL), before we rely on this system for real client data long-term.
THE HOLD-UP
The technical safeguards are already built — the system can already show what data it holds on someone, and delete it on request. But only a qualified lawyer can certify that this satisfies the law. That is a legal judgement, not something engineering can decide on its own.
THE FIX
Send the system for a formal legal review. This step depends entirely on legal team availability, not on any further building — it can run in parallel with Steps 5 to 8.
DRIP Platform — Our Journey, Step by Step
9
Notes: Step 9: close by noting this can run in parallel with the other steps and doesn't block day-to-day team usage — but it does block relying on the system for sensitive real client data long-term.